## User Stories
US #	Create Date	Project	Priority	Status	Title	Description	Assigned	Completed	Deployed	Dependencies	Notes
1	2025/03/19	UI	10	Complete	Setup gitignore	Ensure we are not tracking files that are not part of the project, such as compile results, etc.	mturner	2025/03/25
16	2025/03/25	UI	10	Complete	Make a dev branch and begin using it.	Make a dev branch and begin using it.	mturner	2025/03/25
2	2025/03/19	UI	5	Complete	Make mobile first	Do whatever is necessary to make the site responsive and display correctly on a phone.	mturner	2025/03/25
3	2025/03/19	API	5	Complete	Create API	Create a base API project, with security in place.	mturner	2025/03/25
4	2025/03/19	UI	5	Complete	Make an API call	Make an API call from the UI and display the results	mturner	2025/03/25		3	Created a branch to hold the code at this state as a template for future web/api systems that require auth with access token.
11	2025/03/19	DB	5	Complete	Postgres in a container	Get postgres going in a Docker container	mturner	2025/03/25			Switched from Podman to Docker to reduce effort.
12	2025/03/19	API	6	Complete	Add TypeORM and TSOA to the API	Setup TypeORM and TSOA, and create one entity.	mturner	2025/03/25
15	2025/03/25	UI	6	Complete	Add Tanstack Query	Introduce Tanstack Query to the project for data query and caching.	mturner	2025/03/26
6	2025/03/19	UI, API	5	On Hold	Airplane selection	Add a dropdown near the top of the page to allow the user to select an aircraft. If no aircraft are available, show a message.	mturner
7	2025/03/19	UI, API	5	On Hold	Add aircraft	Add a button near the airplane dropdown to add a new aircraft. Open a dialog and allow the user to enter tail number and description.	mturner
8	2025/03/19	UI, API	5	On Hold	Assign users to aircraft	If the current user is an administrator on the selected aircraft, they should be able to add other users to the aircraft, so they can use it’s log entries.	mturner			9, 3
9	2025/03/19	API	5	In Progress	Add aircraft CRUD to API	Add endpoints to the API to allow CRUD operations.	mturner			3, 11
10	2025/03/19	API	5	On Hold	Add user CRUD	Add endpoints to the API to allow CRUD on users. It should pass appropriate calls to Auth0 if possible. May need to track additional data in the database.	mturner			11
14	2025/03/25	UI, API	5	On Hold	Add logging	Add a logging system	mturner
5	2025/03/19	UI	1	On Hold	Update favicon	Create an icon from the logo and make it the favicon.ico	mturner
13	2025/03/23	API	1	On Hold	Setup environment variables and secrets	Create configuration and environment variable system.	mturner
17	2025/03/25	UI	1	On Hold	Delete the main branch	Delete the main branch from GitHub to reduce confusion, since I’m using master as defualt.	mturner
20250325_1	2025/03/25	UI	2	On Hold	Package site as mobile icon	Figure out how to make the application look like a native app on mobile.	mturner
20250325_2	2025/03/25	UI, API	2	On Hold	Update README.md files	Update README.md files	mturner
20250327_1	2025/03/27	UI	10	In Progress	Investigate dynamic form libraries	The intent is to be able to easily change the forms, probably be able to have versions of forms specific to certain customers.	mturner
20250327_2	2025/03/27	UI, API	5	On Hold	Containerize the API and the UI	Containerize the API and the UI	mturner
20250327_3	2025/03/27	UI, API, DB	6	On Hold	Build a dashboard page	Display status of all jobs.	mturner
20250327_4	2025/03/27	UI, API, DB	4	On Hold	Multiple contacts per owner
20250327_5	2025/03/27	UI, API, DB	4	On Hold	Ability to add notes to an aircraft.	These are mechanic notes that will not go in the logs, but provide history that can be helpful.
20250327_6	2025/03/27	UI, API, DB	4	On Hold	Use FAA API for aircraft and owner info	When adding an aircraft to the system, look-up by tail number and query API for aircraft and owner data. Allow user to approve as-is, or modify, or drop and enter manually.
20250327_7	2025/03/27	UI	4	On Hold	Allow mobile user to scan bar codes	A user on a tablet or phone should be able to scan a bar code or QR code on a part, and add that part to the work order he has open.
20250327_8	2025/03/27	UI	4	On Hold	Allow mobile user to scan bar code on plane	Mechanics should be able to scan themselves in/out of work on a plane, for accurate time keeping. Also allows the software to know which plane and workorder to log parts against.
20250327_9	2025/03/27	UI	2	On Hold	White Labeling	Branding per customer.

## Ideas
Date	Source	Score	Description
03/27/25	mturner	6	Allow for forms to be customized from common templates, per customer.
03/25/25	Mike @ Aces	6	QR or Bar code on the plane. Mechanic scans in/out so we can track time.
03/25/25	Mike @ Aces	7	Dashboard panel that shows status of parts for job. Pre-order, ordered, in-route, arrived. Don’t put the plane in a ready-for-work status until parts have arrived.
03/25/25	Mike @ Aces	5	Each job should be associated with a parts “kit” that includes everything needed for that job.
03/25/25	mturner	5	Parts that need to be ordered could be bundled up by vendor, and possibly integrate with vendor’s ordering system.