## Sheet1
US #	Create Date	Project	Priority	Title	Description	Assigned	Status	Completed	Deployed	Dependencies	Notes
1	2025/03/19	UI	High	Setup gitignore	Ensure we are not tracking files that are not part of the project, such as compile results, etc.	mturner	Complete	2025/03/25
2	2025/03/19	UI	Medium	Make mobile first	Do whatever is necessary to make the site responsive and display correctly on a phone.	mturner	Complete	2025/03/25
3	2025/03/19	API	Medium	Create API	Create a base API project, with security in place.	mturner	Complete	2025/03/25
4	2025/03/19	UI	Medium	Make an API call	Make an API call from the UI and display the results	mturner	Complete	2025/03/25		3	Created a branch to hold the code at this state as a template for future web/api systems that require auth with access token.
5	2025/03/19	UI	Low	Update favicon	Create an icon from the logo and make it the favicon.ico	mturner	On Hold
6	2025/03/19	UI, API	Medium	Airplane selection	Add a dropdown near the top of the page to allow the user to select an aircraft. If no aircraft are available, show a message.	mturner	On Hold
7	2025/03/19	UI, API	Medium	Add aircraft	Add a button near the airplane dropdown to add a new aircraft. Open a dialog and allow the user to enter tail number and description.	mturner	On Hold
8	2025/03/19	UI, API	Medium	Assign users to aircraft	If the current user is an administrator on the selected aircraft, they should be able to add other users to the aircraft, so they can use it’s log entries.	mturner	On Hold			9, 3
9	2025/03/19	API	Medium	Add aircraft CRUD to API	Add endpoints to the API to allow CRUD operations.	mturner	On Hold			3, 11
10	2025/03/19	API	Medium	Add user CRUD	Add endpoints to the API to allow CRUD on users. It should pass appropriate calls to Auth0 if possible. May need to track additional data in the database.	mturner	On Hold			11
11	2025/03/19	DB	Medium	Postgres in a container	Get postgres going in a Docker container	mturner	On Hold				I’ve downloaded the Postgres Docker container, but not yet set it up in Podman.
12	2025/03/19	API	Medium	Add TypeORM and TSOA to the API	Setup TypeORM and TSOA, and create one entity.	mturner	On Hold
13	2025/03/23	API	Low	Setup environment variables and secrets	Create configuration and environment variable system.	mturner	On Hold
14	2025/03/25	UI, API	Medium	Add logging	Add a logging system	mturner	On Hold
15	2025/03/25	UI	Medium	Add Tanstack Query	Introduce Tanstack Query to the project for data query and caching.	mturner	On Hold